## Sheet1
Relocation Planning Sheet
| Assigned To | Status | Due Date | Next Steps | Comments
TWELVE WEEKS BEFORE:
Coordination of moving, furniture, and phone
system company along with electrical contractor
Employees to purge their areas
SIX WEEKS BEFORE:
Obtain Insurance Certificate from mover
Notify insurance carrier of relocation
Reserve loading dock & elevators
Order new services (i.e. cleaning)
Order stationary & business cards
FOUR WEEKS BEFORE:
Present building information to employees
Notify vendor re: copier
Notify vendor re: water service
Notify vendor re: postage meter
Notify magazines/newspapers
Notify vendors with standing orders & pick-ups
Notify post office of address change
Notify banks
Notify utilities
Notify insurance companies
Notify copier company for before and after maintenance
Assign move codes
THREE WEEKS BEFORE:
Provide move instructions to employees
Provide recycling bins for file purge
Provide trash bins
Identify locations for packing materials
Update address on website
ONE WEEK BEFORE
Deliver boxes and labels
Distribute access cards
Prepare emergency contact list
Phone training for employees
TWO DAYS BEFORE:
Deliver additional boxes and labels
Label origin and destination for movers
Confirm all vendors and times
Empty and clean out refrigerator and freezer
MOVE DAY/SETTLE-IN:
Explain new functions to employees (i.e. security)
Hang whiteboards/artwork
Remove excess furniture
Remove crates & packing materials
2151 North Dr. Martin Luther King Drive Milwaukee, WI 53212 ¦ Phone: 414.372.7000 ¦ chcoakley.com